## Sprint 1
User story: General Website Features |  |  |  |  | Story Points: 6 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments | Current Velocity | Sprint Tasks | Total Tasks
6 | 6.1 | Create Homepage template | 1 | 1 | Ben | 1916-08-28 |  | Undefined | 15 | 15
| 6.2 | Create Event page template | 1 | 2 | Ben | 2016-01-09 | ///(template with style sheet avalibe 28/09/16)
| 6.3 | Create General Account page template | 1 | 0.5 | Ben | 2016-01-09 | ///(template with style sheet avalibe 28/09/16)
| 6.4 | Create Admin login page | 1 | 0.5 | Ben | 2016-01-09 | ///(template with style sheet avalibe 28/09/16)
| 6.5 | Allow Website interactivity (click tabs, change webpages) | 0.5 | 0.5 | Ben | 1916-08-28
| 6.6 | Over all website style (css, html body) | 36 | 25 | Ben | 1916-08-28
User story: Social Media Integration |  |  |  |  | Story Points: 4 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
1 | 1.1 | Use appropriate plugins to connect the user's facebook account to the website | 1 | 5 | Ben | 1916-08-28
| 1.2 | Send notifications to users facebook page from the website facebook | 2 |  | Facebook | 2016-02-09 | (can't be created by website) this is an automated fetaure of facebook /// User would recive notifcation through
| 1.3 | [5 empty] | Moved to new event planning user story in Sprint 2
| 1.4 | Test if plugin is working by sending notifications | 1 | 1 | Ben (facebook twiter) | 2016-01-09
and emails to accessible facebook twiter and email account
| 1.5 | Create Socail Media accounts | 1 | 1 | Ben | 1916-08-28
User story: Comment Section |  |  |  |  | Story Points: 1 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
11 | 11.1 | Use appropriate plugins to allow users to post comments on the event pages | 0.5 | 1 | Ben | 2016-01-09 | (facebook)
| 11.2 | Display the already posted comments | 0.5 | 1 | Ben | 1916-08-28 | (facebook / twitter)
User story: Sponsors Advertising |  |  |  |  | Story Points: 2 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
12 | 12.1 | Add and remove sponsors to an event | 3 | 1 | Ben | 2016-01-09 | ///faked in html though ///Finalised in database user story
| 12.2 | Display sponsors ads on webpages | 1 | 0.5 | Ben | 2016-01-09
| 12.3 | Build Slide show for ads in html/javascript | 2 | 1 | Ben | 2016-01-09
User story: |  |  |  |  | Story Points: | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
Link for older revisions
https://docs.google.com/spreadsheets/d/13qp7GBObVRwCOuKaldAYDRk46rpQ0ARoLywaFVi5zPs/edit?usp=sharing

## Sprint 2
User story: Database |  |  |  |  | Story Points: 6 |  | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments | Current Velocity | Sprint Tasks | Total Tasks
21 | 21.1 | Create virtual computer to load files on | 5 | 5 | Glynn | 2016-01-09 |  | 13 | 24 | 39
| 21.2 | Test Virtual computer functionality | 1 | 1 | Glynn | 2016-01-09 | //Rather than creating a dedicated server
| 21.3 | Create Registered Members table | 1 | 1 | GLynn | 1916-09-16 | // Does not contain all columns. but can be added later
| 21.4 | Create Committee Planner table | 1 | 1 | Glynn | 1916-09-16 | // Does not contain all columns. but can be added later
| 21.5 | Create Sponsors table | 1 | 1 | Glynn | 1916-09-17
| 21.6 | Create Volunteers table | 1 | 1 | Glynn | 1916-09-17
| 21.7 | Create Events table | 1 | 1 | Glynn | 1916-09-17
| 21.8 | Load HTML to virtual computer | 1 | 1 | Glynn | 2016-01-09 | // Loaded templates
| 21.9 | Connect database to website | 10 | 10 | Glynn | 1916-09-17 | // Works if the proper queries are used to connect to the database
User story: Event Planning |  |  |  |  | Story Points: 2 |  | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
20 | 20.1 | Query search to retrieve all emails from registered members table | 0.5 | 0.5 | Glynn | 1916-09-17
| 20.2 | Display all registered members emails | 0.5 | 0.5 | Glynn | 1916-09-17
| 20.3 | Send Email containing event details to all members | 0.5 | 0.5 | Glynn | 1916-09-17 | Was thinking of just making it manual. As in just send an email to a bunch of dummy addresses, through one of our emails
| 20.4 | See if they arrived | 0.5 | 0.5 | Glynn | 1916-09-17
User story: FAQ |  |  |  |  | Story Points: 1 |  | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
5 | 5.1 | Write code containing the FAQs entries | 0.5 |  | Lance |  | //Make as just a flat html messages
| 5.2 | Display the FAQ entries on the website | 0.5 |  | Lance
User story: Profile Management |  |  |  |  | Story Points: 4 |  | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
8 | 8.1 | Create login page | 1 | 1 | Glynn | 1916-09-16
| 8.2 | After a match display account details | 1 | 1 | Glynn | 1916-09-16
| 8.3 | Make account details editable | 1 | 1 | Glynn | 1916-09-16
| 8.4 | When editting account details, ask to enter password again | 1 | 1 | Glynn | 1916-09-17 | // yes but the re-entry field isnt hidden... still works though
| 8.5 | Make sure edits are saved back to database | 0.5 | 0.5 | Glynn | 1916-09-16
User story: Track Events |  |  |  |  | Story Points: 3 |  | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
4 | 4.1 | Load google map extension onto html | 5 | 5 | Ben | 1916-09-17
| 4.2 | Set location of google map, to location of event | 5 | 5 | Ben | 1916-09-17
| 4.3 | Query search to retrieve event information | 1 |  | Lance
| 4.4 | Display important information (Location, time of event, date) on event page | 1 |  | Lance |  | //Just as text on html page

## Sprint 3
User story: Finish login |  |  |  |  | Story Points: 1 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments | Total Task | Total story points
22 | 22.1 | Format login text boxes and buttons to match design | 0.5 | 0.5 | Glynn | 2016-09-22 |  | 92 | 22
| 22.2 | Connect Homepage login tab to login file | 1 | 1 | Glynn | 2016-09-22
| 22.3 | Test functionality (drop down box, buttons, links) | 0.5 | 1 | Glynn | 2016-09-22
User story: Add new sponsors |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
33 | 33.1 | Create form with proper textboxes, labels, buttons etc. | 1 |  | Lance(In progress)
| 33.2 | Connect to database and save as new entry on confirm | 1 |  | Lance(In progress)
| 33.3 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Lance(In progress)
| 33.4 | Connect to the other pages on design (tab links and navigation) | 1 |  | Lance(In progress)
| 33.5 | Test functionality (drop down box, buttons, links) | 0.5 |  | Lance(In progress)
User story: List all sponsors |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
34 | 34.1 | Create page with labels and buttons to match design | 0.5 |  | Ben(InProgress)
| 34.2 | Connect to databse to pull entries | 0.5 |  | Ben(InProgress)
| 34.3 | Write sql queires to retrieve required data | 1 |  | Ben(InProgress)
| 34.4 | Display on page | 0.5 |  | Ben(InProgress)
| 34.5 | Format page to match design (tabs on top, logo, display of information etc.) | 2 |  | Ben(InProgress)
| 34.6 | Connect to the other pages on design (tab links and navigation) | 1 |  | Ben(InProgress)
| 34.7 | Test functionality (drop down box, buttons, links) | 0.5 |  | Ben(InProgress)
User story: Sponsor's donation history |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
35 | 35.1 | If the table doesn’t exists. Create table for sponsors donations | 0.5 |  | Ben(InProgress)
| 35.2 | Create page with labels and buttons to match design | 0.5 |  | Ben(InProgress)
| 35.3 | Connect to databse to pull entries | 0.5 |  | Ben(InProgress)
| 35.4 | Write sql queires to retrieve required data | 1 |  | Ben(InProgress)
| 35.5 | Display on page | 0.5 |  | Ben(InProgress)
| 35.6 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Ben(InProgress)
| 35.7 | Connect to the other pages on design (tab links and navigation) | 1 |  | Ben(InProgress)
| 35.8 | Test functionality (drop down box, buttons, links) | 0.5 |  | Ben(InProgress)
User story: Log new sponsor's donation |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
40 | 40.1 | If the table doesn’t exists. Create table for sponsors donations | 0.5 |  | Ben(InProgress)
| 40.2 | Create form with textboxes and buttons to match design | 2 |  | Ben(InProgress)
| 40.3 | Connect to databse | 0.5 |  | Ben(InProgress)
| 40.4 | Write sql queires to add entry to table | 1 |  | Ben(InProgress)
| 40.5 | Update table with new entry on confirm | 1 |  | Ben(InProgress)
| 40.6 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Ben(InProgress)
| 40.7 | Connect to the other pages on design (tab links and navigation) | 1 |  | Ben(InProgress)
| 40.8 | Test functionality (drop down box, buttons, links) | 0.5 |  | Ben(InProgress)
User story: Members account registry |  |  |  |  | Story Points: 3 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
23 | 23.1 | Create login account form with proper textboxes, labels etc. | 1 | 1 | Glynn | 2016-09-24
| 23.2 | Create account details form with proper textboxes, labels etc. | 1 | 1 | Glynn | 2016-09-24
| 23.3 | Connect to database | 0.5 | 0.5 | Glynn | 2016-09-24
| 23.4 | Write sql queires to add entry to table | 2 | 2 | Glynn | 2016-09-24
| 23.5 | Update table with new entry on confirm | 2 | 2 | Glynn | 2016-09-24
| 23.6 | Format page to match design (tabs on top, logo, display of information etc.) | 1 | 1 | Glynn | 2016-09-24
| 23.7 | Connect to the other pages on design (tab links and navigation) | 2 | 2 | Glynn | 2016-09-24
| 23.8 | Test functionality (drop down box, buttons, links) | 0.5 | 0.5 | Glynn | 2016-09-24
User story: Volunteer's list |  |  |  |  | Story Points: 2 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
3 | 3.1 | Create page with labels and buttons to match design | 2 | 2 | Glynn | 2016-10-07
| 3.2 | Connect to databse | 0.5 | 0.5 | Glynn | 2016-10-07
| 3.3 | Write sql queires to pull information from table | 1 | 1 | Glynn | 2016-10-07
| 3.4 | Display pulled information on page | 0.5 | 0.5 | Glynn | 2016-10-07
| 3.5 | Format page to match design (tabs on top, logo, display of information etc.) | 2 | 2 | Glynn | 2016-10-07 | Added save button
| 3.6 | Connect to the other pages on design (tab links and navigation) | 1 | 1 | Glynn | 2016-10-07
| 3.7 | Test functionality (drop down box, buttons, links) | 0.5 | 0.5 | Glynn | 2016-10-07
User story: Register new volunteer |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
41 | 41.1 | Create form with textboxes and buttons to match design | 1 |  | Lance(In progress)
| 41.2 | Connect to databse | 0.5 |  | Lance(In progress)
| 41.3 | Write sql queires to add entry to table | 1 |  | Lance(In progress)
| 41.4 | Update table with new entry on confirm | 1 |  | Lance(In progress)
| 41.5 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Lance(In progress)
| 41.6 | Connect to the other pages on design (tab links and navigation) | 1 |  | Lance(In progress)
| 41.7 | Test functionality (drop down box, buttons, links) | 0.5 |  | Lance(In progress)
User story: Edit account details |  |  |  |  | Story Points: 1 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
25 | 25.1 | Create form with textboxes and buttons to match design | 1 | 1 | Glynn | 2016-09-23
| 25.2 | Connect to databse | 0.5 | 0.5 | Glynn | 2016-09-23
| 25.3 | Write sql queires to update table on confirm | 1 | 1 | Glynn | 2016-09-23
| 25.4 | Format page to match design (tabs on top, logo, display of information etc.) | 1 | 1 | Glynn | 2016-09-23
| 25.5 | Connect to the other pages on design (tab links and navigation) | 1 | 1 | Glynn | 2016-09-23
| 25.6 | Test functionality (drop down box, buttons, links) | 0.5 | 0.5 | Glynn | 2016-09-23
User story: edit login details |  |  |  |  | Story Points: 3 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
26 | 26.1 | Create verificiation form with textboxes and buttons | 1 | 1 | Glynn | 2016-09-23
| 26.2 | Create edit login form with textboxes and buttons to match design | 1 | 1 | Glynn | 2016-09-23
| 26.3 | Connect to databse | 0.5 | 0.5 | Glynn | 2016-09-23
| 26.4 | Connect edit button to the two new forms | 2 | 2 | Glynn | 2016-09-23
| 26.5 | Write code for verification form | 2 | 2 | Glynn | 2016-09-23
| 26.6 | Write sql queires to update table on cofirm | 2 | 2 | Glynn | 2016-09-23
| 26.7 | Format page to match design (tabs on top, logo, display of information etc.) | 1 | 1 | Glynn | 2016-09-23
| 26.8 | Connect to the other pages on design (tab links and navigation) | 1 | 1 | Glynn | 2016-09-23
| 26.9 | Test functionality (drop down box, buttons, links, queries, code) | 0.5 | 0.5 | Glynn | 2016-09-23
User story: view account |  |  |  |  | Story Points: 1 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
27 | 27.1 | Create page with labels and buttons to match design | 2 | 2 | Glynn | 2016-09-23
| 27.2 | Connect to databse | 0.5 | 0.5 | Glynn | 2016-09-23
| 27.3 | Write sql queires to pull information from table | 1 | 1 | Glynn | 2016-09-23
| 27.4 | Display pulled information on page | 0.5 | 0.5 | Glynn | 2016-09-23
| 27.5 | Format page to match design (tabs on top, logo, display of information etc.) | 2 | 2 | Glynn | 2016-09-23
| 27.6 | Connect to the other pages on design (tab links and navigation) | 1 | 1 | Glynn | 2016-09-23
| 27.7 | Test functionality (drop down box, buttons, links) | 0.5 | 0.5 | Glynn | 2016-09-23
User story: View event |  |  |  |  | Story Points: 4 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
4 | 4.1 | Create page with labels and buttons to match design | 2 | 2 | Glynn | 2016-10-05
| 4.2 | Connect to databse | 0.5 | 0.5 | Glynn | 2016-10-05
| 4.3 | Write sql queires to pull information from table | 1 | 1 | Glynn | 2016-10-05
| 4.4 | Display pulled information on page | 0.5 | 0.5 | Glynn | 2016-10-05
| 4.5 | Write code to show/hide features depending on account | 2 | 2 | Glynn | 2016-10-05
| 4.6 | Apply google map extension as the map | 2 | 2 | Glynn | 2016-10-05 | Used a different api than what ben used. As in I had to use my own api key, which in bens api didn’t need. Not really a big deal, but just saying.
| 4.7 | Make the map extension show the location pulled | 2 | 2 | Glynn | 2016-10-05
| 4.8 | Format page to match design (tabs on top, logo, display of information etc.) | 2 | 2 | Glynn | 2016-10-07 | Doesn’t display the planners of the event. Still need to make planners event table.
| 4.9 | Connect to the other pages on design (tab links and navigation) | 1 | 1 | Glynn | 2016-10-05 | Essentially yes. The main problem is the initial page to be displayed, in the planners page isnt built yet.
| 4,10 | Test functionality (drop down box, buttons, links) | 0.5 | 0.5 | Glynn | 2016-10-05 | But if you manually open the event page, it should load with the hidden features. It will just use the data from previous pages.
User story: List all planners |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
30 | 27.1 | Create page with labels and buttons to match design | 2 |  | Lance(In progress)
| 27.2 | Connect to databse | 0.5 |  | Lance(In progress)
| 27.3 | Write sql queires to pull information from table | 1 |  | Lance(In progress)
| 27.4 | Display pulled information on page | 0.5 |  | Lance(In progress)
| 27.5 | Format page to match design (tabs on top, logo, display of information etc.) | 2 |  | Lance(In progress)
| 27.6 | Connect to the other pages on design (tab links and navigation) | 1 |  | Lance(In progress)
| 27.7 | Test functionality (drop down box, buttons, links) | 0.5 |  | Lance(In progress)
User story:Events attending |  |  |  |  | Story Points: 2 | Statues: Done
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
32 | 32.1 | Create page with labels and buttons to match design | 1 | 1 | Glynn | 2016-10-05
| 32.2 | Connect to databse | 0.5 | 0.5 | Glynn | 2016-10-05
| 32.3 | Write sql queires to pull information from table | 2 | 2 | Glynn | 2016-10-05
| 32.4 | Display pulled information on page | 0.5 | 0.5 | Glynn | 2016-10-05
| 32.5 | Format page to match design (tabs on top, logo, display of information etc.) | 3 | 3 | Glynn | 2016-10-05 | Also added the tickets reserved
| 32.6 | Connect to the other pages on design (tab links and navigation) | 1 | 1 | Glynn | 2016-10-05
| 32.7 | Test functionality (drop down box, buttons, links) | 0.5 | 0.5 | Glynn | 2016-10-05

## Sprint 4
User story: Add new sponsors |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
33 | 33.1 | Create form with proper textboxes, labels, buttons etc. | 1 |  | Lance(In progress)
| 33.2 | Connect to database and save as new entry on confirm | 1 |  | Lance(In progress)
| 33.3 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Lance(In progress)
| 33.4 | Connect to the other pages on design (tab links and navigation) | 1 |  | Lance(In progress)
| 33.5 | Test functionality (drop down box, buttons, links) | 0.5 |  | Lance(In progress)
User story: List all sponsors |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
34 | 34.1 | Create page with labels and buttons to match design | 0.5 |  | Ben(InProgress)
| 34.2 | Connect to databse to pull entries | 0.5 |  | Ben(InProgress)
| 34.3 | Write sql queires to retrieve required data | 1 |  | Ben(InProgress)
| 34.4 | Display on page | 0.5 |  | Ben(InProgress)
| 34.5 | Format page to match design (tabs on top, logo, display of information etc.) | 2 |  | Ben(InProgress)
| 34.6 | Connect to the other pages on design (tab links and navigation) | 1 |  | Ben(InProgress)
| 34.7 | Test functionality (drop down box, buttons, links) | 0.5 |  | Ben(InProgress)
User story: Sponsor's donation history |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
35 | 35.1 | If the table doesn’t exists. Create table for sponsors donations | 0.5 |  | Ben(InProgress)
| 35.2 | Create page with labels and buttons to match design | 0.5 |  | Ben(InProgress)
| 35.3 | Connect to databse to pull entries | 0.5 |  | Ben(InProgress)
| 35.4 | Write sql queires to retrieve required data | 1 |  | Ben(InProgress)
| 35.5 | Display on page | 0.5 |  | Ben(InProgress)
| 35.6 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Ben(InProgress)
| 35.7 | Connect to the other pages on design (tab links and navigation) | 1 |  | Ben(InProgress)
| 35.8 | Test functionality (drop down box, buttons, links) | 0.5 |  | Ben(InProgress)
User story: Log new sponsor's donation |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
40 | 40.1 | If the table doesn’t exists. Create table for sponsors donations | 0.5 |  | Ben(InProgress)
| 40.2 | Create form with textboxes and buttons to match design | 2 |  | Ben(InProgress)
| 40.3 | Connect to databse | 0.5 |  | Ben(InProgress)
| 40.4 | Write sql queires to add entry to table | 1 |  | Ben(InProgress)
| 40.5 | Update table with new entry on confirm | 1 |  | Ben(InProgress)
| 40.6 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Ben(InProgress)
| 40.7 | Connect to the other pages on design (tab links and navigation) | 1 |  | Ben(InProgress)
| 40.8 | Test functionality (drop down box, buttons, links) | 0.5 |  | Ben(InProgress)
User story: Register new volunteer |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
41 | 41.1 | Create form with textboxes and buttons to match design | 1 |  | Lance(In progress)
| 41.2 | Connect to databse | 0.5 |  | Lance(In progress)
| 41.3 | Write sql queires to add entry to table | 1 |  | Lance(In progress)
| 41.4 | Update table with new entry on confirm | 1 |  | Lance(In progress)
| 41.5 | Format page to match design (tabs on top, logo, display of information etc.) | 1 |  | Lance(In progress)
| 41.6 | Connect to the other pages on design (tab links and navigation) | 1 |  | Lance(In progress)
| 41.7 | Test functionality (drop down box, buttons, links) | 0.5 |  | Lance(In progress)
User story: List all planners |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
30 | 27.1 | Create page with labels and buttons to match design | 2 |  | Lance(In progress)
| 27.2 | Connect to databse | 0.5 |  | Lance(In progress)
| 27.3 | Write sql queires to pull information from table | 1 |  | Lance(In progress)
| 27.4 | Display pulled information on page | 0.5 |  | Lance(In progress)
| 27.5 | Format page to match design (tabs on top, logo, display of information etc.) | 2 |  | Lance(In progress)
| 27.6 | Connect to the other pages on design (tab links and navigation) | 1 |  | Lance(In progress)
| 27.7 | Test functionality (drop down box, buttons, links) | 0.5 |  | Lance(In progress)
User story: List all planners |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
30 | 27.1 | Create page with labels and buttons to match design | 2 |  | Lance(In progress)
| 27.2 | Connect to databse | 0.5 |  | Lance(In progress)
| 27.3 | Write sql queires to pull information from table | 1 |  | Lance(In progress)
| 27.4 | Display pulled information on page | 0.5 |  | Lance(In progress)
| 27.5 | Format page to match design (tabs on top, logo, display of information etc.) | 2 |  | Lance(In progress)
| 27.6 | Connect to the other pages on design (tab links and navigation) | 1 |  | Lance(In progress)
| 27.7 | Test functionality (drop down box, buttons, links) | 0.5 |  | Lance(In progress)
User story: Available events |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
24 | 24.1 | Create page with labels and buttons to match design | 2 |  | Glynn
| 24.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 24.3 | Write PHP code to display the required information | 2 |  | Glynn
| 24.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 24.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Event Registration |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
18 | 18.1 | Create page with labels and buttons to match design | 1 |  | Glynn
| 18.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 18.3 | Write PHP code to display the required information | 2 |  | Glynn
| 18.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 18.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Member's donation history |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
2 | 2.1 | Create page with labels and buttons to match design | 2 |  | Glynn
| 2.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 2.3 | Write PHP code to display the required information | 2 |  | Glynn
| 2.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 2.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Member's new donation |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
31 | 31.1 | Create page with labels and buttons to match design | 0.5 |  | Glynn
| 31.2 | Write sql queires to pull information from table | 0.5 |  | Glynn
| 31.3 | Write PHP code to display the required information | 1 |  | Glynn
| 31.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 31.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Financial Tracking |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
9 | 9.1 | Create page with labels and buttons to match design | 2 |  | Glynn
| 9.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 9.3 | Write PHP code to summarize financial details | 2 |  | Glynn
| 9.4 | Write PHP code to display the required information | 2 |  | Glynn
| 9.5 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 9.6 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Planners Events |  |  |  |  | Story Points: 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
36 | 36.1 | Create page with labels and buttons to match design | 2 |  | Glynn
| 36.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 36.3 | Write PHP code to display the required information | 2 |  | Glynn
| 36.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 36.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Plan more events |  |  |  |  | Story Points: 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
37 | 37.1 | Create page with labels and buttons to match design | 2 |  | Glynn
| 37.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 37.3 | Write PHP code to display the required information | 2 |  | Glynn
| 37.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 37.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Create Events |  |  |  |  | 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
38 | 38.1 | Create page with labels and buttons to match design | 2 |  | Glynn
| 38.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 38.3 | Write PHP code to display the required information | 2 |  | Glynn
| 38.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 38.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Edit Event Details |  |  |  |  | 2 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
28 | 28.1 | Create page with labels and buttons to match design | 2 |  | Glynn
| 28.2 | Write sql queires to pull information from table | 1 |  | Glynn
| 28.3 | Write PHP code to display the required information | 2 |  | Glynn
| 28.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 28.5 | Test functionality (drop down box, buttons, links) | 1 |  | Glynn
User story: Email |  |  |  |  | 4 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
39 | 39.1 | Create page with labels and buttons to match design | 3 |  | Glynn
| 39.2 | Write sql queires to pull information from table | 3 |  | Glynn
| 39.3 | Write PHP code to display differentiate which accounts to email | 4 |  | Glynn
| 39.4 | Connect to the other pages on design (tab links and navigation) | 0.5 |  | Glynn
| 39.5 | Test that emails are sent and received | 1 |  | Glynn
User story: Stop Planning event |  |  |  |  | 1 | Statues: Ongoing
Story ID | Task ID | Task Description | Estimate Time | Taken TIme | Completed By | Completed On | Comments
29 | 29.1 | Finish hyperlink from events page | 1 |  | Glynn