## Sprint 1
User story: General Website Features |  |  |  | Story Points: 6 | Statues: Ongoing | Ledgend
Task ID | Task Description | Estimate Time | Taken TIme | Task Assigned to: | Estimated delivery date |  | Must have to continue progress
1 | Create Homepage template | 1 | 1 | Ben | 28/08/16 |  | Unassiagned
2 | Create Event page template ///(template with style sheet avalibe 28/09/16) | 1 | 2 | Ben | 2016-01-09
3 | Create General Account page template ///(template with style sheet avalibe 28/09/16) | 1 | 0.5 | Ben | 2016-01-09
4 | Create Admin login page ///(template with style sheet avalibe 28/09/16) | 1 | 0.5 | Ben | 2016-01-09
5 | Allow Website interactivity (click tabs, change webpages) | 0.5 | 0.5 | Ben | 28/08/16
6 | Over all website style (css, html body) | 36 | 25 | Ben | 28/08/16
User story: Social Media Integration |  |  |  | Story Points: 4 | Statues: Ongoing
Task ID | Task Description | Estimate Time | Taken TIme | Task Assigned to: | Estimated delivery date
7 | Use appropriate plugins to connect the user's facebook account to the website | 1 | 5 | Ben | 28/08/18
8 | Send notifications to users facebook page from the website/// User would recive notifcation through facebook (can't be created by website) this is an automated fetaure of facebook | 2 |  | Facebook | 2009
9 | Send emails are sent from the website to all users ///requires Database and accounts | 3
10 | Test if plugin is working by sending notifications | 1 | 1 | Ben (facebook twiter) | 2016-01-09
and emails to accessible facebook twiter and email account ///requires DB
16 | Create Socail Media accounts | 1 | 1 | Ben | 28/08/18
User story: Comment Section |  |  |  | Story Points: 1 | Statues: Ongoing
Task ID | Task Description | Estimate Time | Taken TIme | Task Assigned to: | Estimated delivery date
11 | Use appropriate plugins to allow users to post comments on the event pages (facebook) | 0.5 | 1 | Ben | 2016-01-09
12 | Display the already posted comments (facebook / twitter) | 0.5 | 1 | Ben | 28/08/16
User story: Sponsors Advertising |  |  |  | Story Points: 2 | Statues: Ongoing
Task ID | Task Description | Estimate Time | Taken TIme | Task Assigned to: | Estimated delivery date
13 | Add and remove sponsors to an event ///faked in html though | 3 | 1 | Ben | 2016-01-09
14 | Display sponsors ads on webpages | 1 | 0.5 | Ben | 2016-01-09
15 | Build Slide show for ads in html/javascript | 2 | 1 | Ben | 2016-01-09
User story: |  |  |  | Story Points: | Statues: Ongoing
Task ID | Task Description | Estimate Time | Taken TIme | Task Assigned to: | Estimated delivery date

## Sprint 2
User story: Database |  |  |  | Story Points: 6 | Statues: Ongoing
Task ID | Task Description | Estimate Time | Taken TIme | Task Assigned to: | Estimated delivery date
17 | Create virtual computer to load files on //Rather than creating a dedicated server | 5 | 5 | Glynn | 2016-01-09
18 | Test Virtual computer functionality | 1 | 1 | Glynn | 2016-01-09
19 | Create Account details table | 1
20 | Create Sponsors table | 1
21 | Create Volunteers table | 1
22 | Create Events table | 1
23 | Load HTML to virtual computer // Loaded templates | 1 | 1 | Glynn | 2016-01-09
24 | Connect database to website // As in have access to all tables, and display on html as needed. -- might be added to individual page tasks | 10